# LIFT 2026 timeline/schedule

March

3/16: Theron and Shauna meet 6-7

3/17: RFP written (complete)

3/20: RFP PUBLIC

April

4/3: RFP DUE, Theron and Shauna meet 5-6PM

4/10: Lift rubrics due from Artist Selection Committee

4/14: 3-4PM ASC meeting option 1

4/16: 6-7PM ASC meeting option 2

4/17: Artist selections announced to artists, public

4/20: 5:30-7:30 Artist onboarding meeting with Shauna

May

5/1: Rough draft designs due to Church and Shauna

5/4: Church design selection complete, artists and Shauna notified 
5/15: Final designs due to church and Shauna
5/16-5/31: Murals completed

7/1-7/11: Murals removed