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March
3/16: Theron and Shauna meet 6-7
3/17: RFP written (complete)
3/20: RFP PUBLIC

April
4/3: RFP DUE, Theron and Shauna meet 5-6PM
4/10: Lift rubrics due from Artist Selection Committee
4/14: 3-4PM ASC meeting option 1
4/16: 6-7PM ASC meeting option 2
4/17: Artist selections announced to artists, public
4/20: 5:30-7:30 Artist onboarding meeting with Shauna 

May
5/1: Rough draft designs due to Church and Shauna
5/4: Church design selection complete, artists and Shauna notified 
5/15: Final designs due to church and Shauna
5/16-5/31: Murals completed
7/1-7/11: Murals removed







